## lookup
github | bts
svk31 | pay.svk
wmbutler | billbutler
calvinfroedge | calvin-froedge
ariesjia | ares-chen
rrandom | emanon-h
tylerfletcher914 | firecrab-witness
happyconcepts | sell-bitcoin
ppitonak | paliboyqqq
xiangxn | necklace
startailcoon | sc-pay
mattbeckman | netdragonx-pay
izmlam | zhaomu8
bigspider | spider-1
efork | efork-1
dot5enko | dot5enko-pay
cryptopeppe | cryptopeppe3
maiopirata | m1i0p1r1t1
HarukaMa | haruka
xeroc | blockchainprojects
pnomolos | pnomolos-1
kennybll | kennybll-accnt
diogogomes | diogogomes-eu
oxarbitrage | oxarbitrage.a699
pavel-lipcean | lpavel20
zhyupe | zhyupe
nbcks | nickbuckner3
ahdigital | dom-0
gibbsfromncis | gibbs-from-ncis
kapeer42 | kapeer-42
austinamoruso | austin-amoruso
swoopyy | swoopyyy7
xeroc | blockchainprojects
sschiessl-bcp | blockchainprojects
vaniyokk | vaniyokk69
gn1github | gn1
tbapi-0ka | tbapi-0ka
clockworkgr | clockwork

## 170901
Task | Github Account | BTS Account | Hours | Payment
188 | svk31 | pay.svk | 1 | 125
289 | happyconcepts | sell-bitcoin | 1.5 | 187.5
49 | calvinfroedge | calvin-froedge | 7 | 875
327 | svk31 | pay.svk | 1 | 125
94 | calvinfroedge | calvin-froedge | 4 | 500
291 | tylerfletcher914 | firecrab-witness | 1 | 125
318 | svk31 | pay.svk | 2.5 | 312.5
313 | svk31 | pay.svk | 1 | 125
263 | svk31 | pay.svk | 0.5 | 62.5
215 | skenan | skenan-bitshares | 3 | 375
202 | svk31 | pay.svk | 10 | 1250
305 | ariesjia | ares-chen | 0.5 | 62.5
85 | svk31 | pay.svk | 7 | 875
254 | hyper-bola | para-shd | 4 | 500
275 | ariesjia | ares-chen | 1 | 125
110 | calvinfroedge | calvin-froedge | 1 | 125
276 | calvinfroedge | calvin-froedge | 0.5 | 62.5
139 | calvinfroedge | calvin-froedge | 1 | 125
160 | calvinfroedge | calvin-froedge | 0.5 | 62.5
66 | calvinfroedge | calvin-froedge | 1 | 125
191 | svk31 | pay.svk | 1 | 125
201 | svk31 | pay.svk | 6 | 750
220 | svk31 | pay.svk | 1 | 125
260 | svk31 | pay.svk | 0.5 | 62.5
237 | ariesjia | ares-chen | 1 | 125
211 | rrandom | emanon-h | 1 | 125
265 | ariesjia | ares-chen | 0.5 | 62.5
235 | ariesjia | ares-chen | 2 | 250
47 | calvinfroedge | calvin-froedge | 1.5 | 187.5
236 | ariesjia | ares-chen | 0.5 | 62.5
253 | svk31 | pay.svk | 1 | 125
252 | calvinfroedge | calvin-froedge | 1.5 | 187.5
163 | calvinfroedge | calvin-froedge | 2 | 250
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 8 | 1000
Total |  |  |  | 13312.5
Due |  |  |  | 2017-08-31
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 170901
Budget |  |  |  | 11250
Overage |  |  |  | 2062.5

## 170914
Task | Github Account | BTS Account | Hours | Payment
364 | calvinfroedge | calvin-froedge | 2.5 | 312.5
311 | calvinfroedge | calvin-froedge | 3 | 375
392 | hyper-bola | para-shd | 0.25 | 31.25
403 | svk31 | pay.svk | 1.5 | 187.5
321 | calvinfroedge | calvin-froedge | 2 | 250
315 | fletcher914 | firecrab-witness | 4 | 500
385 | ariesjia | ares-chen | 0.5 | 62.5
374 | ariesjia | ares-chen | 0.5 | 62.5
43 | calvinfroedge | calvin-froedge | 4 | 500
53 | svk31 | pay.svk | 4 | 500
390 | calvinfroedge | calvin-froedge | 0.5 | 62.5
351 | calvinfroedge | calvin-froedge | 2 | 250
314 | svk31 | pay.svk | 6 | 750
342 | svk31 | pay.svk | 1 | 125
279 | calvinfroedge | calvin-froedge | 4 | 500
279 | svk31 | pay.svk | 2 | 250
224 | svk31 | pay.svk | 18 | 2250
200 | svk31 | pay.svk | 7 | 875
366 | svk31 | pay.svk | 0.5 | 62.5
358 | happyconcepts | sell-bitcoin | 0.5 | 62.5
204 | svk31 | pay.svk | 0.5 | 62.5
292 | svk31 | pay.svk | 1 | 125
186 | svk31 | pay.svk | 0.5 | 62.5
334 | ariesjia | ares-chen | 1 | 125
345 | skenan | skenan-bitshares | 0.25 | 31.25
346 | svk31 | pay.svk | 1 | 125
304 | svk31 | pay.svk | 1 | 125
337 | calvinfroedge | calvin-froedge | 1 | 125
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 8 | 1000
Total |  |  |  | 13500
Due |  |  |  | 2017-08-31
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 170901
Budget |  |  |  | 11250
Overage |  |  |  | 2250
Cumulative Overage |  |  |  | 4312.5

## 171001
Task | Github Account | BTS Account | Hours | Payment
341 | happyconcepts | billbutler | 0.25 | 31.25 | Repay billbutler for advance
480 | svk31 | pay.svk | 0.75 | 93.75
417 | ariesjia | ares-chen | 0.25 | 31.25
460 | ariesjia | ares-chen | 1 | 125
446 | svk31 | pay.svk | 0.25 | 31.25
464 | svk31 | pay.svk | 0.25 | 31.25
457 | svk31 | pay.svk | 0.25 | 31.25
429 | ariesjia | ares-chen | 0.25 | 31.25
116 | svk31 | pay.svk | 0.25 | 31.25
440 | svk31 | pay.svk | 0.5 | 62.5
261 | svk31 | pay.svk | 1.5 | 187.5
248 | svk31 | pay.svk | 1.5 | 187.5
402 | svk31 | pay.svk | 0.5 | 62.5
370 | svk31 | pay.svk | 1 | 125
175 | svk31 | pay.svk | 0.5 | 62.5
434 | svk31 | pay.svk | 0.25 | 31.25
433 | svk31 | pay.svk | 0.5 | 62.5
411 | svk31 | pay.svk | 0.25 | 31.25
154 | svk31 | pay.svk | 1 | 125
416 | svk31 | pay.svk | 2 | 250
376 | svk31 | pay.svk | 3 | 375
418 | svk31 | pay.svk | 0.25 | 31.25
435 | svk31 | pay.svk | 0.25 | 31.25
426 | svk31 | pay.svk | 0.25 | 31.25
393 | svk31 | pay.svk | 2 | 250
424 | svk31 | pay.svk | 1 | 125
414 | svk31 | pay.svk | 1 | 125
409 | svk31 | pay.svk | 0.5 | 62.5
408 | svk31 | pay.svk | 0.25 | 31.25
407 | svk31 | pay.svk | 0.25 | 31.25
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 8 | 1000
Total |  |  |  | 7468.75
Due |  |  |  | 2017-10-02
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 171001
Budget |  |  |  | 11250
Overage |  |  |  | -3781.25
Cumulative Overage |  |  |  | 531.25

## 171015
Task | Github Account | BTS Account | Hours | Payment
522 | svk31 | pay.svk | 0.25 | 31.25
486 | svk31 | pay.svk | 1 | 125
258 | svk31 | pay.svk | 6 | 750
517 | svk31 | pay.svk | 1 | 125
508 | ppitonak | paliboyqqq | 0.25 | 31.25
454 | bigspider | spider-1 | 6 | 750
506 | svk31 | pay.svk | 0.5 | 62.5
494 | svk31 | pay.svk | 0.25 | 31.25 | paid to asha-man and svk, requested refund from svk
493 | svk31 | pay.svk | 0.25 | 31.25
492 | svk31 | pay.svk | 0.25 | 31.25
489 | svk31 | pay.svk | 0.25 | 31.25
476 | svk31 | pay.svk | 0.25 | 31.25
496 | calvinfroedge | calvin-froedge | 2 | 250
578 | svk31 | pay.svk | 0.25 | 31.25
543 | calvinfroedge | calvin-froedge | 1 | 125
563 | svk31 | pay.svk | 0.5 | 62.5
571 | svk31 | pay.svk | 2 | 250
479 | svk31 | pay.svk | 1 | 125
574 | svk31 | pay.svk | 0.25 | 31.25
562 | abitmore | abit | 1.5 | 187.5
488 | svk31 | pay.svk | 2 | 250
294 | svk31 | pay.svk | 1.5 | 187.5
484 | calvinfroedge | calvin-froedge | 1 | 125
507 | calvinfroedge | calvin-froedge | 3 | 375
551 | svk31 | pay.svk | 0.5 | 62.5
573 | svk31 | pay.svk | 0.25 | 31.25
444 | xiangxn | necklace | 4 | 500 | refunded from svk
501 | svk31 | pay.svk | 0.25 | 31.25
531 | svk31 | pay.svk | 2 | 250
482 | svk31 | pay.svk | 0.25 | 31.25
500 | svk31 | pay.svk | 0.25 | 31.25
533 | calvinfroedge | calvin-froedge | 0.5 | 62.5
462 | svk31 | pay.svk | 2 | 250
70 | svk31 | pay.svk | 1 | 125
547 | calvinfroedge | calvin-froedge | 2 | 250
497 | svk31 | pay.svk | 0.5 | 62.5
529 | svk31 | pay.svk | 0.5 | 62.5
483 | svk31 | pay.svk | 0.25 | 31.25
471 | svk31 | pay.svk | 0.1 | 12.5
378 | svk31 | pay.svk | 24 | 3000
528 | svk31 | pay.svk | 0.5 | 62.5
527 | svk31 | pay.svk | 0.25 | 31.25
545 | svk31 | pay.svk | 1 | 125
549 | calvinfroedge | calvin-froedge | 1 | 125
553 | svk31 | pay.svk | 0.25 | 31.25
490 | svk31 | pay.svk | 0.25 | 31.25
535 | svk31 | pay.svk | 0.25 | 31.25
536 | svk31 | pay.svk | 0.25 | 31.25
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 8 | 1000
Total |  |  |  | 14043.75
Due |  |  |  | 2017-08-31
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 171015
Budget |  |  |  | 11250
Overage |  |  |  | 2793.75
Cumulative Overage |  |  |  | 3325

## 171101
Task | Github Account | BTS Account | Hours | Payment
634 | svk31 | pay.svk | 1 | 125
530 | startailcoon | sc-pay | 2 | 250
673 | svk31 | pay.svk | 0.1 | 12.5
644 | NA | #N/A | 0 | 0
670 | svk31 | pay.svk | 0.75 | 93.75
538 | svk31 | pay.svk | 20 | 2500
579 | svk31 | pay.svk | 1 | 125
52 | svk31 | pay.svk | 0.25 | 31.25
581 | svk31 | pay.svk | 1 | 31.25
632 | startailcoon | sc-pay | 1 | 125
623 | izmlam | zhaomu8 | 2 | 250
302 | svk31 | pay.svk | 1.5 | 187.5
658 | startailcoon | sc-pay | 0.25 | 31.25
598 | startailcoon | sc-pay | 0.25 | 31.25
627 | startailcoon | sc-pay | 0.5 | 62.5
633 | startailcoon | sc-pay | 0.25 | 31.25
455 | svk31 | pay.svk | 0.5 | 62.5
645 | startailcoon | sc-pay | 0.1 | 12.5
430 | svk31 | pay.svk | 4 | 500
622 | happyconcepts | sell-bitcoin | 0.5 | 62.5
625 | startailcoon | sc-pay | 0.1 | 12.5
580 | happyconcepts | sell-bitcoin | 0.5 | 62.5
590 | happyconcepts | sell-bitcoin | 0.1 | 12.5
607 | mattbeckman | netdragonx-pay | 0.25 | 31.25
615 | svk31 | pay.svk | 0.25 | 31.25
586 | svk31 | pay.svk | 0.5 | 62.5
605 | svk31 | pay.svk | 0.25 | 31.25
583 | svk31 | pay.svk | 2 | 250
576 | svk31 | pay.svk | 0.25 | 31.25
594 | mattbeckman | netdragonx-pay | 0.5 | 62.5
592 | svk31 | pay.svk | 0.25 | 31.25
589 | svk31 | pay.svk | 1 | 125
587 | svk31 | pay.svk | 0.1 | 12.5
498 | svk31 | pay.svk | 0.25 | 31.25
585 | svk31 | pay.svk | 0.1 | 12.5
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 8 | 1000
Total |  |  |  | 10075
Due |  |  |  | 2017-08-31
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 171015
Budget |  |  |  | 11250
Overage |  |  |  | -1175
Cumulative Overage |  |  |  | 2150

## 171121
Task | Github Account | BTS Account | Hours | Payment
677 | svk31 | pay.svk | 0.25 | 31.25
635 | svk31 | pay.svk | 1.5 | 187.5
651 | startailcoon | sc-pay | 9 | 1125
676 | wmbutler | billbutler | 0.1 | 12.5
739 | svk31 | pay.svk | 0.25 | 31.25
158 | calvinfroedge | calvin-froedge | 2 | 250
705 | mattbeckman | netdragonx-pay | 2 | 250
719 | startailcoon | sc-pay | 0.25 | 31.25
689 | mattbeckman | netdragonx-pay | 1 | 31.25
725 | svk31 | pay.svk | 0.75 | 93.75
693 | startailcoon | sc-pay | 0.5 | 62.5
695 | startailcoon | sc-pay | 0.5 | 62.5
724 | svk31 | pay.svk | 0.5 | 62.5
708 | svk31 | pay.svk | 0.5 | 62.5
702 | startailcoon | sc-pay | 0.25 | 31.25
654 | bigspider | spider-1 | 1 | 125
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 8 | 1000
Total |  |  |  | 7200
Due |  |  |  | 2017-11-25
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 171121
Budget |  |  |  | 11250
Overage |  |  |  | -4050
Cumulative Overage |  |  |  | -1900

## 171205
Task | Github Account | BTS Account | Hours | Payment
722 | startailcoon | sc-pay | 0.25 | 31.25
684 | svk31 | pay.svk | 0.1 | 12.5
774 | calvinfroedge | calvin-froedge | 1.5 | 187.5
167 | efork | efork-1 | 1.5 | 187.5
698 | calvinfroedge | calvin-froedge | 1.5 | 187.5
771 | mattbeckman | netdragonx-pay | 5 | 625
556 | startailcoon | sc-pay | 8 | 1000
765 | dot5enko | dot5enko-pay | 0.5 | 62.5
781 | startailcoon | sc-pay | 2 | 250
723 | startailcoon | sc-pay | 0.1 | 12.5
738 | startailcoon | sc-pay | 0.25 | 31.25
630 | svk31 | pay.svk | 10 | 1250
763 | svk31 | pay.svk | 1 | 125
558 | calvinfroedge | calvin-froedge | 3 | 375
718 | calvinfroedge | calvin-froedge | 0.5 | 62.5
762 | svk31 | pay.svk | 1 | 125
732 | startailcoon | sc-pay | 0.25 | 31.25
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 10 | 1250
Total |  |  |  | 9556.25
Due |  |  |  | 2017-11-25
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 171205
Budget |  |  |  | 11250
Overage |  |  |  | -1693.75
Cumulative Overage |  |  |  | -3593.75

## 171219
Task | Github Account | BTS Account | Hours | Payment
804 | wmbutler | billbutler | 2.5 | 312.5 | Repay Bill from personal funds for https://github.com/bitshares/bitshares-ui/issues/804
639 | maiopirata | m1i0p1r1t1 | 5.25 | 656.25
875 | svk31 | pay.svk | 0.5 | 62.5
800 | dot5enko | dot5enko-pay | 1 | 125
874 | svk31 | pay.svk | 0.5 | 62.5
831 | dot5enko | dot5enko-pay | 1 | 125
868 | svk31 | pay.svk | 3 | 375
843 | svk31 | pay.svk | 0.25 | 31.25
647 | dot5enko | dot5enko-pay | 2 | 250
819 | bigspider | spider-1 | 0.5 | 62.5
796 | dot5enko | dot5enko-pay | 0.5 | 62.5
833 | dot5enko | dot5enko-pay | 0.25 | 31.25
791 | startailcoon | sc-pay | 0.25 | 31.25
807 | startailcoon | sc-pay | 0.1 | 12.5
452 | svk31 | pay.svk | 3 | 375
803 | dot5enko | dot5enko-pay | 0.5 | 62.5
799 | dot5enko | dot5enko-pay | 0.1 | 12.5
813 | dot5enko | dot5enko-pay | 0.25 | 31.25
798 | xeroc | blockchainprojects | 0.1 | 12.5
777 | svk31 | pay.svk | 0.25 | 31.25
861 | harukama | haruka | 0.25 | 31.25
811 | svk31 | pay.svk | 0.25 | 31.25
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 10 | 1250
Total |  |  |  | 7787.5
Due |  |  |  | 2017-12-27
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 171205
Budget |  |  |  | 11250
Overage |  |  |  | -3462.5
Cumulative Overage |  |  |  | -7056.25
https://github.com/bitshares/bitshares-ui/issues/804 |  |  |  | Bill paid from personal funds |  | 2.5

## 180108
Task | Github Account | BTS Account | Hours | Payment
557 | startailcoon | sc-pay | 11.5 | 1437.5
900 | pnomolos | pnomolos-1 | 1 | 125
727 | startailcoon | sc-pay | 2 | 250
631 | svk31 | pay.svk | 0.5 | 62.5
911 | kennybll | kennybll-accnt | 3 | 375
956 | startailcoon | sc-pay | 0.25 | 31.25
828 | dot5enko | dot5enko-pay | 5 | 625
921 | harukama | haruka | 1 | 125
938 | zhyupe | zhyupe | 0.25 | 31.25
893 | pnomolos | pnomolos-1 | 1.5 | 187.5
773 | oxarbitrage | oxarbitrage.a699 | 20 | 2500
667 | diogogomes | diogogomes-eu | 4 | 500
883 | dot5enko | dot5enko-pay | 1.25 | 156.25
823 | dot5enko | dot5enko-pay | 2 | 250
929 | kennybll | kennybll-accnt | 0.5 | 62.5
927 | svk31 | pay.svk | 0.5 | 62.5
733 | startailcoon | sc-pay | 3.5 | 437.5
919 | startailcoon | sc-pay | 0.5 | 62.5
916 | svk31 | pay.svk | 2 | 250
759 | pavel-lipcean | lpavel20 | 6 | 750
787 | pavel-lipcean | lpavel20 | 2 | 250
1000 | calvinfroedge | calvin-froedge | 2 | 250
804 | cryptopeppe | cryptopeppe3 | 2.5 | 312.5
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 10 | 1250
Total |  |  |  | 14093.75 | Original 9093.75
Due |  |  |  | 2018-01-12
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 180108
Budget |  |  |  | 11250
Overage |  |  |  | 2843.75
Cumulative Overage |  |  |  | -4212.5

## 180115
Task | Github Account | BTS Account | Hours | Payment
973 | pnomolos | pnomolos-1 | 2 | 250
888 | dot5enko | dot5enko-pay | 5.5 | 687.5
996 | zhyupe | zhyupe | 0.25 | 31.25
994 | nbcks | nickbuckner3 | 0.5 | 62.5
991 | zhyupe | zhyupe | 0.5 | 62.5
980 | dot5enko | dot5enko-pay | 1 | 125
985 | dot5enko | dot5enko-pay | 1 | 125
992 | harukama | haruka | 1 | 125
997 | svk31 | pay.svk | 0.5 | 62.5
945 | pnomolos | pnomolos-1 | 1 | 125
1001 | startailcoon | sc-pay | 1 | 125
901 | pnomolos | pnomolos-1 | 0.5 | 62.5
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 10 | 1250
Total |  |  |  | 6843.75
Due |  |  |  | 2018-01-22
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 180115
Budget |  |  |  | 11250
Overage |  |  |  | -4406.25
Cumulative Overage |  |  |  | -8618.75

## 180201
Task | Github Account | BTS Account | Hours | Payment
1004 | mattbeckman | netdragonx-pay | 3 | 375
1039 | ahdigital | dom-0 | 2.5 | 312.5
1094 | mattbeckman | netdragonx-pay | 0.5 | 62.5
1028 | gibbsfromncis | gibbs-from-ncis | 2 | 250
972 | kapeer42 | kapeer-42 | 3 | 375
977 | kapeer42 | kapeer-42 | 3 | 375
1068 | gibbsfromncis | gibbs-from-ncis | 0.25 | 31.25
1071 | gibbsfromncis | gibbs-from-ncis | 0.25 | 31.25
1027 | harukama | haruka | 1 | 125
1024 | harukama | haruka | 1 | 125
1025 | harukama | haruka | 1 | 125
1073 | ahdigital | dom-0 | 2 | 250
744 | startailcoon | sc-pay | 7.5 | 937.5
1035 | ahdigital | dom-0 | 2.75 | 343.75
1036 | dot5enko | dot5enko-pay | 2 | 250
1054 | ahdigital | dom-0 | 1 | 125
1050 | ahdigital | dom-0 | 0.5 | 62.5
1011 | svk31 | pay.svk | 1 | 125
1059 | svk31 | pay.svk | 3 | 375
1013 | pnomolos | pnomolos-1 | 1.5 | 187.5
937 | zhyupe | zhyupe | 2.5 | 312.5
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 10 | 1250
Total |  |  |  | 10156.25
Due |  |  |  | 2018-02-06
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 180201
Budget |  |  |  | 11250
Overage |  |  |  | -1093.75
Cumulative Overage |  |  |  | -9712.5

## 180215
Task | Github Account | BTS Account | Hours | Payment
1138 | ahdigital | dom-0 | 2 | 250
686 | gibbsfromncis | gibbs-from-ncis | 6 | 750
904 | gibbsfromncis | gibbs-from-ncis | 5 | 625
1130 | gibbsfromncis | gibbs-from-ncis | 1 | 125
889 | startailcoon | sc-pay | 13.5 | 1687.5
993 | austinamoruso | austin-amoruso | 5 | 625
1158 | startailcoon | sc-pay | 0.25 | 31.25
1139 | ahdigital | dom-0 | 6 | 750
1007 | zhyupe | zhyupe | 6 | 750
1144 | swoopyy | swoopyyy7 | 3 | 375
1114 | ashaman | #N/A | 0.25 | 31.25
1147 | svk31 | pay.svk | 1 | 125
887 | dot5enko | dot5enko-pay | 1.5 | 187.5
1107 | ahdigital | dom-0 | 1.5 | 187.5
1090 | ahdigital | dom-0 | 1 | 125
1091 | gibbsfromncis | gibbs-from-ncis | 1.5 | 187.5
1061 | gibbsfromncis | gibbs-from-ncis | 1 | 125
1099 | pnomolos | pnomolos-1 | 0.25 | 31.25
1043 | startailcoon | sc-pay | 1 | 125
1056 | nbcks | nickbuckner3 | 1 | 125
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 16 | 2000
Total |  |  |  | 12968.75
Due |  |  |  | 2018-02-18
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 180215
Budget |  |  |  | 11250
Overage |  |  |  | 1718.75
Cumulative Overage |  |  |  | -7993.75

## 180302
Task | Github Account | BTS Account | Hours | Payment
1150 | xeroc | blockchainprojects | 5 | 625
588 | calvinfroedge | calvin-froedge | 44.5 | 5562.5
588 | startailcoon | sc-pay | 3 | 375
691 | zhyupe | zhyupe | 4 | 500
766 | nbcks | nickbuckner3 | 1.5 | 187.5
1002 | pnomolos | pnomolos-1 | 4 | 500
1069 | gibbsfromncis | gibbs-from-ncis | 0.5 | 62.5
1149 | svk31 | pay.svk | 1.5 | 187.5
1211 | ahdigital | dom-0 | 1 | 125
1234 | ahdigital | dom-0 | 0.25 | 31.25
1240 | svk31 | pay.svk | 2 | 250
1195 | startailcoon | sc-pay | 0.5 | 62.5
1229 | svk31 | pay.svk | 1 | 125
1030 | diogogomes | diogogomes-eu | 2 | 250
1217 | startailcoon | sc-pay | 0.5 | 62.5
1179 | startailcoon | sc-pay | 2 | 250
1178 | startailcoon | sc-pay | 1 | 125
332 | gn1github | gn1 | 5 | 625
1186 | ahdigital | dom-0 | 0.5 | 62.5
1177 | pnomolos | pnomolos-1 | 0.5 | 62.5
1070 | startailcoon | sc-pay | 1 | 125
1220 | svk31 | pay.svk | 1.5 | 187.5
1215 | vaniyokk | vaniyokk69 | 0.25 | 31.25
1133 | austinamoruso | austin-amoruso | 1 | 125
1219 | svk31 | pay.svk | 0.25 | 31.25
1218 | svk31 | pay.svk | 0.25 | 31.25
1082 | ahdigital | dom-0 | 6 | 750
1134 | ahdigital | dom-0 | 0.5 | 62.5
754 | harukama | haruka | 0.5 | 62.5
1201 | svk31 | pay.svk | 0.25 | 31.25
1083 | ahdigital | dom-0 | 0.5 | 62.5
1136 | gibbsfromncis | gibbs-from-ncis | 2 | 250
261 | svk31 | pay.svk | 1.5 | 187.5
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 16 | 2000
Total |  |  |  | 17718.75
Due |  |  |  | 2018-03-04
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 180302
Budget |  |  |  | 16000
Overage |  |  |  | 1718.75
Cumulative Overage |  |  |  | 1718.75

## 180315
Task | Github Account | BTS Account | Hours | Payment
1213 | ahdigital | dom-0 | 3 | 375
984 | tbapi-0ka | #N/A | 2 | 250
1272 | svk31 | pay.svk | 1 | 125
1222 | swoopyy | swoopyyy7 | 0.5 | 62.5
1256 | gibbsfromncis | gibbs-from-ncis | 0.5 | 62.5
1271 | gibbsfromncis | gibbs-from-ncis | 1 | 125
450 | gibbsfromncis | gibbs-from-ncis | 1 | 125
17 | gibbsfromncis | gibbs-from-ncis | 5 | 625
1265 | gibbsfromncis | gibbs-from-ncis | 0.25 | 31.25
1277 | startailcoon | sc-pay | 4 | 500
1255 | gibbsfromncis | gibbs-from-ncis | 1 | 125
1281 | svk31 | pay.svk | 0.5 | 62.5
1258 | gibbsfromncis | gibbs-from-ncis | 0.5 | 62.5
1278 | sschiessl-bcp | blockchainprojects | 1 | 125
568 | startailcoon | sc-pay | 5 | 625
1194 | svk31 | pay.svk | 1 | 125
981 | startailcoon | sc-pay | 1.5 | 187.5
1243 | startailcoon | sc-pay | 2.5 | 312.5
969 | startailcoon | sc-pay | 8 | 1000
1248 | startailcoon | sc-pay | 0.5 | 62.5
1260 | svk31 | pay.svk | 4 | 500
1245 | startailcoon | sc-pay | 1 | 125
1268 | calvinfroedge | calvin-froedge | 0.5 | 62.5
1261 | svk31 | pay.svk | 0.1 | 12.5
1189 | ahdigital | dom-0 | 2 | 250
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 16 | 2000
Total |  |  |  | 11668.75
Due |  |  |  | 2018-03-16
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 180315
Budget |  |  |  | 16000
Overage |  |  |  | -4331.25
Cumulative Overage |  |  |  | -2612.5

## 180401
Task | Github Account | BTS Account | Hours | Payment
1374 | svk31 | pay.svk | 0 | 0
1373 | svk31 | pay.svk | 1 | 125
1338 | svk31 | pay.svk | 10 | 1250
999 | gibbsfromncis | gibbs-from-ncis | 2 | 250
1341 | svk31 | pay.svk | 2 | 250
1342 | harukama | haruka | 0.25 | 31.25
1371 | svk31 | pay.svk | 2 | 250
1026 | ahdigital | dom-0 | 3 | 375
1026 | gibbsfromncis | gibbs-from-ncis | 1 | 125
1331 | gibbsfromncis | gibbs-from-ncis | 1.5 | 187.5
1344 | calvinfroedge | calvin-froedge | 0.5 | 62.5
1223 | startailcoon | sc-pay | 8 | 1000
1223 | ahdigital | dom-0 | 2.5 | 312.5
1289 | calvinfroedge | calvin-froedge | 1.25 | 156.25
1299 | startailcoon | sc-pay | 8 | 1000
1190 | ahdigital | dom-0 | 1.5 | 187.5
1190 | calvinfroedge | calvin-froedge | 2 | 250
1337 | calvinfroedge | calvin-froedge | 0.25 | 31.25
1364 | svk31 | pay.svk | 1 | 125
1173 | gibbsfromncis | gibbs-from-ncis | 3 | 375
984 | tbapi-0ka | tbapi-0ka | 2 | 250
1335 | startailcoon | sc-pay | 1.5 | 187.5
1110 | ahdigital | dom-0 | 0.5 | 62.5
1110 | pnomolos | pnomolos-1 | 2 | 250
1349 | svk31 | pay.svk | 1 | 125
1343 | svk31 | pay.svk | 4 | 500
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 16 | 2000
Total |  |  |  | 13468.75
Due |  |  |  | 2018-04-03
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 180401
Budget |  |  |  | 16000
Overage |  |  |  | -2531.25
Cumulative Overage |  |  |  | -5143.75

## 180418
Task | Github Account | BTS Account | Hours | Payment
1333 | gibbsfromncis | gibbs-from-ncis | 11 | 1375
895 | ahdigital | dom-0 | 5 | 625
1372 | sschiessl-bcp | blockchainprojects | 1.5 | 187.5
1420 | startailcoon | sc-pay | 1 | 125
1417 | startailcoon | sc-pay | 5 | 625
1384 | startailcoon | sc-pay | 5 | 625
1411 | startailcoon | sc-pay | 8 | 1000
1415 | startailcoon | sc-pay | 0.1 | 12.5
1396 | startailcoon | sc-pay | 1 | 125
1375 | startailcoon | sc-pay | 1.5 | 187.5
1395 | startailcoon | sc-pay | 1 | 125
1388 | svk31 | pay.svk | 0.25 | 31.25
1367 | svk31 | pay.svk | 0.5 | 62.5
1367 | happyconcepts | sell-bitcoin | 0.5 | 62.5
1275 | startailcoon | sc-pay | 5 | 625
1244 | startailcoon | sc-pay | 5 | 625
1376 | svk31 | pay.svk | 0.1 | 12.5
1334 | gibbsfromncis | gibbs-from-ncis | 15 | 1875
|  | #N/A |  | 0
|  | #N/A |  | 0
|  | #N/A |  | 0
|  | #N/A |  | 0
|  | #N/A |  | 0
|  | #N/A |  | 0
|  | #N/A |  | 0
|  | #N/A |  | 0
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 16 | 2000
Total |  |  |  | 14056.25
Due |  |  |  | 2018-04-22
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 180418
Budget |  |  |  | 16000
Overage |  |  |  | -1943.75
Cumulative Overage |  |  |  | -7087.5

## 180501
Task | Github Account | BTS Account | Hours | Payment
1435 | ahdigital | dom-0 | 5 | 625
998 | ahdigital | dom-0 | 1.5 | 187.5
1329 | ahdigital | dom-0 | 12 | 1500
1455 | svk31 | pay.svk | 2 | 250
1446 | tbapi-0ka | tbapi-0ka | 0.5 | 62.5
1469 | happyconcepts | sell-bitcoin | 0.5 | 62.5
1481 | sschiessl-bcp | blockchainprojects | 3 | 375
1481 | svk31 | pay.svk | 0.5 | 62.5
1369 | happyconcepts | sell-bitcoin | 1.5 | 187.5
1284 | ahdigital | dom-0 | 4 | 500
1228 | sschiessl-bcp | blockchainprojects | 10 | 1250
1478 | svk31 | pay.svk | 0.25 | 31.25
905 | svk31 | pay.svk | 15 | 1875
1449 | ahdigital | dom-0 | 10 | 1250
1328 | svk31 | pay.svk | 1.5 | 187.5
1379 | ahdigital | dom-0 | 4 | 500
1379 | startailcoon | sc-pay | 7 | 875
1276 | startailcoon | sc-pay | 5 | 625
1207 | startailcoon | sc-pay | 1.5 | 187.5
1319 | mattbeckman | netdragonx-pay | 1 | 125
1464 | svk31 | pay.svk | 4 | 500
1336 | ahdigital | dom-0 | 10 | 1250
1406 | svk31 | pay.svk | 1 | 125
1432 | svk31 | pay.svk | 1 | 125
1440 | mattbeckman | netdragonx-pay | 4 | 500
1263 | diogogomes | diogogomes-eu | 2 | 250
1454 | startailcoon | sc-pay | 0.5 | 62.5
1453 | startailcoon | sc-pay | 0.5 | 62.5
1451 | svk31 | pay.svk | 1 | 125
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 16 | 2000
Total |  |  |  | 19468.75
Due |  |  |  | 2018-05-16
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 180501
Budget |  |  |  | 16000
Overage |  |  |  | 3468.75
Cumulative Overage |  |  |  | -3618.75

## 180525
Task | Github Account | BTS Account | Hours | Payment
1447 | tbapi-0ka | tbapi-0ka | 8 | 1000
1532 | startailcoon | sc-pay | 1 | 125
1448 | gibbsfromncis | gibbs-from-ncis | 1 | 125
1512 | gibbsfromncis | gibbs-from-ncis | 4 | 500
1502 | svk31 | pay.svk | 16 | 2000
1527 | svk31 | pay.svk | 0.5 | 62.5
1533 | svk31 | pay.svk | 0.5 | 62.5
1535 | startailcoon | sc-pay | 0.75 | 93.75
1534 | startailcoon | sc-pay | 0.5 | 62.5
1528 | svk31 | pay.svk | 2 | 250
1482 | kapeer42 | kapeer-42 | 10 | 1250
1397 | happyconcepts | sell-bitcoin | 3 | 375
1517 | clockworkgr | clockwork | 1 | 125
1516 | startailcoon | sc-pay | 0.5 | 62.5
1520 | startailcoon | sc-pay | 1 | 125
1437 | kapeer42 | kapeer-42 | 12 | 1500
1437 | svk31 | pay.svk | 1 | 125
1515 | svk31 | pay.svk | 1.5 | 187.5
1475 | startailcoon | sc-pay | 2 | 250
905 | svk31 | pay.svk | 24 | 3000
1466 | ahdigital | dom-0 | 2 | 250
1463 | svk31 | pay.svk | 0.5 | 62.5
1288 | kapeer42 | kapeer-42 | 1 | 125
Sprint Management | wmbutler | billbutler | 30 | 3750
Code Review | svk31 | pay.svk | 16 | 2000
Total |  |  |  | 17468.75
Due |  |  |  | 2018-05-30
Remittance Address |  |  |  | bitshares-ui
Currency |  |  |  | bitUSD
Invoice Number |  |  |  | 180525
Budget |  |  |  | 16000
Overage |  |  |  | 1468.75
Cumulative Overage |  |  |  | -2150