## Weeks 14-15
User | Date | Notes | Task | Time | HourlyRate | Amount
Abit More | 2018-04-03 | WIP on PR 641 - BSIP 35 : rounding issue in market engine | Development | 4 | 150 | 600
Abit More | 2018-04-05 | WIP on PR 641 Market engine improvements for #342 rounding issue and #672 call order update issue | Development | 4 | 150 | 600
Abit More | 2018-04-07 | Split PR #641 (market engine changes) into #827, #829 and #830. | Development | 4 | 150 | 600
Abit More | 2018-04-08 | BSIP 38 development | Development | 4 | 150 | 600
Abit More | 2018-04-09 | Core PR #829 BSIP31-34: check review feedback and explain / make changes | Development | 1 | 150 | 150
Abit More | 2018-04-09 | Core PR #829 BSIP31-34: add new test case | Development | 2 | 150 | 300
Abit More | 2018-04-10 | BSIP38 document update and coding. | Development | 1 | 150 | 150
Abit More | 2018-04-10 | BSIP38 document update and coding. | Development | 2 | 150 | 300
Abit More | 2018-04-11 | BSIP38 doc update and coding | Development | 2 | 150 | 300
Abit More | 2018-04-12 | BSIP38 test cases. | Development | 1 | 150 | 150
Abit More | 2018-04-12 | BSIP31-34 code update after review; BSIP38 test cases. | Development | 3 | 150 | 450
Abit More | 2018-04-13 | BSIP38 coding and testing. | Development | 4 | 150 | 600
Abit More | 2018-04-15 | bsip38 testing | Development | 2 | 150 | 300
Abit More | 2018-04-15 | bsip38 testing | Development | 2 | 150 | 300
Abit More Total | [5 empty] | 5400
Alfredo Garcia | 2018-04-02 | Coordination of Release 180328, last 2 weeks. | Development | 4 | 150 | 600
Alfredo Garcia | 2018-04-04 | meeting with ryan fox | Meeting | 1 | 150 | 150
Alfredo Garcia Total | [5 empty] | 750
Fabian Schuh | 2018-04-03 | backend development for a new plugin | Development | 3 | 150 | 450
Fabian Schuh | 2018-04-11 | improving pending_transactions api | Development | 0.98333 | 150 | 147.5
Fabian Schuh Total | [5 empty] | 597.5
John M. Jones | 2018-04-09 | Ubuntu 18.04 LTS testing | Development | 1 | 125 | 125
John M. Jones | 2018-04-11 | Boost 1.66 diagnostics | Development | 3 | 125 | 375
John M. Jones | 2018-04-12 | Diagnose test failure for OpenSSL 1.1 PR | Development | 2 | 125 | 250
John M. Jones | 2018-04-12 | Boost 1.66 operation_tests failure research | Development | 3 | 125 | 375
John M. Jones | 2018-04-12 | Mac Segfault Diagnosis | Development | 1 | 125 | 125
John M. Jones Total | [5 empty] | 1250
Mr Taconator | 2018-04-09 | Reviewing escrow discussions | Analysis | 1.5 | 125 | 187.5
Mr Taconator | 2018-04-11 | Reviewing BSIP 35 and 38 | Analysis | 1.5 | 125 | 187.5
Mr Taconator | 2018-04-12 | Escrow BSIP | Analysis | 0.5 | 125 | 62.5
Mr Taconator | 2018-04-12 | Commenting on BSIP 38 and reviewing open Github issues | Analysis | 0.5 | 125 | 62.5
Mr Taconator | 2018-04-14 | Editing BSIP 38 | Analysis | 3.5 | 125 | 437.5
Mr Taconator | 2018-04-15 | Escrow BSIP | Analysis | 3 | 125 | 375
Mr Taconator Total | [5 empty] | 1312.5
Peter Conrad | 2018-04-03 | fc #23 #33 #36 | Review | 1.1 | 150 | 165
Peter Conrad | 2018-04-03 | fc #36 | Review | 1.3667 | 150 | 205
Peter Conrad | 2018-04-06 |  | Review | 1.0667 | 150 | 160
Peter Conrad | 2018-04-07 |  | Review | 0.5 | 150 | 75
Peter Conrad | 2018-04-08 | Core #829 | Review | 1.85 | 150 | 277.5
Peter Conrad | 2018-04-08 | Core #827 #828 #829 | Review | 1.0333 | 150 | 155
Peter Conrad | 2018-04-08 | Core #829 | Review | 0.96667 | 150 | 145
Peter Conrad | 2018-04-09 | CORE #829 #804 #832 FC #38 | Review | 1.45 | 150 | 217.5
Peter Conrad | 2018-04-09 | FC #36 #38 BSIPS #73 | Review | 0.9 | 150 | 135
Peter Conrad | 2018-04-09 | FC #36/#38 | Review | 2.2833 | 150 | 342.5
Peter Conrad | 2018-04-10 |  | Review | 0.63333 | 150 | 95
Peter Conrad | 2018-04-12 | core #829 | Review | 0.55 | 150 | 82.5
Peter Conrad | 2018-04-12 | BSIP #74 FC #36 CORE #813 #829 #839 #214 | Review | 1.3667 | 150 | 205
Peter Conrad | 2018-04-12 | BSIP 22 Core #829 | Review | 0.33333 | 150 | 50
Peter Conrad | 2018-04-12 | #214 | Programming | 1.4833 | 150 | 222.5
Peter Conrad | 2018-04-12 | #214 | Programming | 1.05 | 150 | 157.5
Peter Conrad Total | [5 empty] | 2690
Ryan R. Fox | 2018-04-02 | GitHub Contribution Guide | Support | 1.5 | 150 | 225
Ryan R. Fox | 2018-04-02 | Timesheets | Support | 1 | 150 | 150
Ryan R. Fox | 2018-04-03 | Continue drafting Contribution Guide. Convert to Wiki doc. Add feedback items. Create gif demos. | Support | 2 | 150 | 300
Ryan R. Fox | 2018-04-03 | Review timesheets and expenses Create invoice, submit | Support | 1 | 150 | 150
Ryan R. Fox | 2018-04-04 | Contribution Guide wiki edits | Support | 1.75 | 150 | 262.5
Ryan R. Fox | 2018-04-04 | Book airfare for SVK to DevCon Confirm details Update with airline Organize seats for Alfredo and SVK | Support | 1 | 150 | 150
Ryan R. Fox | 2018-04-04 | Reimbursement: Airfare for SVK | Reimbursement | 1 | 281.7 | 281.7
Ryan R. Fox | 2018-04-04 | Reimbursement: Airfare for SVK | Reimbursement | 1 | 725.7 | 725.7
Ryan R. Fox | 2018-04-05 | Revise Contribution Guide Review Consensus Changing Release | Support | 3 | 150 | 450
Ryan R. Fox | 2018-04-06 | Add Contribution Guide to Wiki Build [DEMO] Project for Contribution Guide | Support | 3 | 150 | 450
Ryan R. Fox | 2018-04-07 | Present update to BitShares Community on Hangout. | Support | 0.5 | 150 | 75
Ryan R. Fox | 2018-04-08 | Revise Contribution Guide. | Support | 4 | 150 | 600
Ryan R. Fox | 2018-04-09 | Revise Contribution Guide. | Support | 3 | 150 | 450
Ryan R. Fox | 2018-04-10 | Review BSIP35, BSIP38 Revise Contribution Guide | Analysis | 3 | 125 | 375
Ryan R. Fox | 2018-04-11 | Test builds on Ubuntu 18.04 (beta) Test Boost 1.65 revisions | Analysis | 2 | 125 | 250
Ryan R. Fox | 2018-04-12 | Revise Contribution Guide. | Support | 2 | 150 | 300
Ryan R. Fox | 2018-04-15 | Core Team Hotel Shanghai | Reimbursement | 1 | 3093.35 | 3093.35
Ryan R. Fox Total | [5 empty] | 8288.25
Tamami Sugimoto | 2018-04-02 |  | Social Media | 0.5 | 90 | 45
Tamami Sugimoto | 2018-04-02 | Understand issues and research APIs | Analysis | 1.5 | 90 | 135
Tamami Sugimoto | 2018-04-03 | Research BitShares APIs, CIL wallet, Full Node | Analysis | 2.75 | 90 | 247.5
Tamami Sugimoto | 2018-04-04 | Research BitShares Document - duplication | Analysis | 2.5 | 90 | 225
Tamami Sugimoto | 2018-04-05 | research BitShares Overview to prepare and use | Analysis | 2 | 90 | 180
Tamami Sugimoto | 2018-04-05 | Typed and created Quick overview structure to understand BitShares | Analysis | 3 | 90 | 270
Tamami Sugimoto | 2018-04-06 | For Github Documentation | Social Media | 1.75 | 90 | 157.5
Tamami Sugimoto | 2018-04-06 | Public Testne Witness Installation configuration #708 | Analysis | 3.25 | 90 | 292.5
Tamami Sugimoto | 2018-04-07 | create several draft pages in Github | Analysis | 3.5 | 90 | 315
Tamami Sugimoto | 2018-04-08 | research and types draft pages for Github | Analysis | 1.5 | 90 | 135
Tamami Sugimoto | 2018-04-08 | research and draft for Github | Analysis | 2.5 | 90 | 225
Tamami Sugimoto | 2018-04-09 | Github issue and cli-wallet (try and document) | Analysis | 2.5 | 90 | 225
Tamami Sugimoto | 2018-04-10 | Documentation to github repo | Analysis | 2 | 90 | 180
Tamami Sugimoto | 2018-04-11 | Documentation to github | Analysis | 2.25 | 90 | 202.5
Tamami Sugimoto | 2018-04-12 | Documentation to github repo | Analysis | 2.9167 | 90 | 262.5
Tamami Sugimoto | 2018-04-13 | Create Github documents | Analysis | 2.5 | 90 | 225
Tamami Sugimoto | 2018-04-14 | Create Github documents | Analysis | 2.5 | 90 | 225
Tamami Sugimoto | 2018-04-15 | Create Github documents and the structures (about 9hrs) | Analysis | 3 | 90 | 270
Tamami Sugimoto Total | [5 empty] | 3817.5
Grand Total | [5 empty] | 24105.75